AthleteIQ

Sponsor Match Engine

Sprint Plan

2-Day Build — Hour-by-Hour Task Breakdown

v1.0

June 2025

# Sprint Overview

Goal: Ship a fully functional AthleteIQ v1.0 in 2 days (16 working hours). End state: live Vercel deployment with all v1 features working end-to-end.

| Parameter | Value |
| --- | --- |
| Sprint duration | 2 days / 16 hours |
| Team size | 1 developer (solo or pair) |
| Definition of done | Live on Vercel, all 5 features working, no P0 bugs |
| Tech stack | Next.js 14, React, TypeScript, Tailwind, Claude API |

# Day 1 — Foundation (8 Hours)

## Hour 1: Project Setup

- npx create-next-app@latest athleteiq --typescript --tailwind --app

- Install dependencies: npm install docx react-pdf @anthropic-ai/sdk

- Configure .env.local with ANTHROPIC_API_KEY

- Set up src/types/index.ts with all TypeScript interfaces

- Commit: "chore: project scaffold"

## Hour 2: Core Types & Utils

- Define AthleteProfile, AudienceDemographics, SponsorRecommendation in types/index.ts

- Implement promptBuilder.ts — buildPrompt() function

- Implement parseResponse.ts — parseRecommendations() with validation

- Write unit tests for promptBuilder and parseResponse (optional but recommended)

## Hour 3: API Route

- Create src/app/api/match/route.ts

- Implement POST handler: validate body, call Claude API, return parsed JSON

- Add rate limiting middleware (10 RPM per IP)

- Add error handling for timeout, parse failure, API errors

- Test with curl: verify 200 response with 6 recommendations

## Hours 4–5: Athlete & Audience Forms

- Build AthleteForm.tsx: sport selector, career stage, stats textarea, social reach inputs

- Build AudienceForm.tsx: age range, gender split sliders, geo market inputs, interest tags

- Implement form validation (required fields, number ranges)

- Wire forms to shared state (useState or Context)

## Hours 6–7: Results Panel & Sponsor Cards

- Build ResultsPanel.tsx: ranked list of SponsorCard components

- Build SponsorCard.tsx: match score badge, reasoning, audience overlap, pitch angle

- Add copy-to-clipboard button per card

- Add loading skeleton while API call is in flight

- Add error state with retry button

## Hour 8: Save/Load Profiles

- Implement localStorage save: serialize AthleteProfile to JSON, store with key "athleteiq:profiles"

- Build profile selector UI: list saved profiles, click to load into form

- Add delete profile button

- Test: save profile, reload page, verify profile persists and loads correctly

# Day 2 — Polish & Ship (8 Hours)

## Hours 1–2: PDF Export

- Implement ExportButton.tsx using html2canvas + jsPDF or react-pdf

- PDF output: AthleteIQ branding header, athlete name, all 6 sponsor cards

- Test export on Chrome and Firefox

## Hours 3–4: UI Polish

- Apply consistent Tailwind design tokens (colors, spacing, typography)

- Add AthleteIQ logo/wordmark in header

- Ensure mobile responsiveness (test at 375px, 768px, 1280px)

- Add empty states, loading indicators, and success toasts

## Hour 5: End-to-End Testing

- Full happy path: fill forms → submit → receive results → copy pitch → export PDF

- Edge cases: empty optional fields, very long stats text, all social platforms at 0

- API error scenario: test with invalid API key, verify error UI

- Rate limit test: verify 429 response after 10 rapid requests

## Hour 6: Accessibility & Performance

- Add ARIA labels to all form inputs

- Verify keyboard navigation through full form flow

- Run Lighthouse: target Performance > 90, Accessibility > 90

- Optimize any images or heavy imports

## Hour 7: Deployment

- npx vercel — connect to project, deploy to preview

- Set ANTHROPIC_API_KEY in Vercel dashboard environment variables

- Promote preview to production

- Smoke test on production URL

## Hour 8: Documentation & Handoff

- Update README.md with final setup instructions and screenshots

- Tag release: git tag v1.0.0

- Create CHANGELOG.md with feature list

- Share production URL with stakeholders

# Risk Register

| Risk | Probability | Mitigation |
| --- | --- | --- |
| Claude API returns invalid JSON | Medium | parseResponse.ts validates + retries once |
| PDF export broken on Safari | Medium | Test Day 2 H1; fallback to print CSS |
| Rate limit too restrictive | Low | RATE_LIMIT_RPM env var makes it configurable |
| localStorage quota exceeded | Low | Limit saved profiles to 20; show warning |